## Project Work Plan
Activity | Project Lead | Start Date | End Date | Days | weeks
Project Incubation & Topic Refinement | JOSHUA WAMBUA | 01-Sep-2025 | 14-Sep-2025 | 13 | 2
Introduction and Background Study | JOSHUA WAMBUA | 15-Sep-2025 | 05-Oct-2025 | 20 | 3
Literature Review | JOSHUA WAMBUA | 06-Oct-2025 | 09-Nov-2025 | 34 | 5
Problem Definition | JOSHUA WAMBUA | 10-Nov-2025 | 16-Nov-2025 | 7 | 1
Objectives Finalization | JOSHUA WAMBUA | 17-Nov-2025 | 23-Nov-2025 | 7 | 1
Methodology Development | JOSHUA WAMBUA | 24-Nov-2025 | 30-Nov-2025 | 7 | 1
Proposal Writing and Submission | JOSHUA WAMBUA | 01-Dec-2025 | 14-Dec-2025 | 14 | 2
Proposal Presentation | JOSHUA WAMBUA | 15-Dec-2025 | 21-Dec-2025 | 6 | 1
System Architecture & Design | JOSHUA WAMBUA | 05-Jan-2026 | 25-Jan-2026 | 20 | 3
Hardware Design & Integration | JOSHUA WAMBUA | 26-Jan-2026 | 16-Feb-2026 | 21 | 4
Firmware Development | JOSHUA WAMBUA | 10-Feb-2026 | 10-Mar-2026 | 28 | 5
Cloud and Database Integration | JOSHUA WAMBUA | 01-Mar-2026 | 22-Mar-2026 | 21 | 4
Web Application Development | JOSHUA WAMBUA | 10-Mar-2026 | 05-Apr-2026 | 26 | 4
Machine Learning Integration | JOSHUA WAMBUA | 23-Mar-2026 | 05-Apr-2026 | 14 | 2
Testing & Documentation | JOSHUA WAMBUA | 06-Apr-2026 | 25-Apr-2026 | 19 | 3
Presentation & Submission | JOSHUA WAMBUA | 26-Apr-2026 | 30-Apr-2026 | 4 | 1
start date | 01-Sep-2025 | 45901
end date | 30-Apr-2026 | 46142